## Estimation_AdminWeb_20161117
AIMS Web Admin
Time is estmate for a senior to do the work and fully unit test
Screen / Feature Name(s) | Feature Name | Priority | Best Case | Most Likely | Worst Case | Time Left | Notes | P1 B | P1 M | P1 W | P1 A | P2 B | P2 M | P2 W | P2 A
Documentation | Technical Design Document Addendum | 1 | 8 | 8 | 8 | 0 | Create TDD with screen shots | 8 | 8 | 8 |  | 0 | 0 | 0
Documentation | API Spec P1 | 1 | 16 | 16 | 16 | 4 |  | 16 | 16 | 16 |  | 0 | 0 | 0
Documentation | API Spec P2 | 2 | 16 | 16 | 16 |  |  | 0 | 0 | 0 |  | 16 | 16 | 16
Organization | Create | 1 | 8 | 10 | 12 | 0 |  | 8 | 10 | 12 |  | 0 | 0 | 0
Group | Create | 1 | 8 | 10 | 16 | 0 |  | 8 | 10 | 16 |  | 0 | 0 | 0
User | Create | 1 | 8 | 10 | 16 | 0 |  | 8 | 10 | 16 |  | 0 | 0 | 0
Authentication | Login | 1 | 8 | 10 | 16 | 0 |  | 8 | 10 | 16 |  | 0 | 0 | 0
Survey | Create | 1 | 16 | 24 | 32 | 0 |  | 16 | 24 | 32 |  | 0 | 0 | 0
Survey | Read | 1 | 8 | 10 | 16 | 1 | Display all surveys the user has created (searchable / sortable), and if an individual survey is selected, display details. | 8 | 10 | 16 |  | 0 | 0 | 0
Survey | Edit | 1 | 10 | 12 | 16 | 0 |  | 10 | 12 | 16 |  | 0 | 0 | 0
Survey | Delete | 1 | 10 | 12 | 16 | 5 |  | 10 | 12 | 16 |  | 0 | 0 | 0
Authentication | Logout | 1 | 1 | 2 | 3 | 0 |  | 1 | 2 | 3 |  | 0 | 0 | 0
Organization | Read | 1 | 4 | 6 | 8 | 0 | Display all Organizaitons (searchable), and if an individual org is selected, display details. | 4 | 6 | 8 |  | 0 | 0 | 0
Organization | Edit | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
Organization | Delete | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
Group | Read | 1 | 4 | 6 | 8 | 0 | Display all Groups, and if an individual group is selected, Display all users in the group and their roles. Admin can add users to group from here. | 4 | 6 | 8 |  | 0 | 0 | 0
Group | Edit | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
Group | Delete | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
User | Read | 1 | 8 | 10 | 16 | 0 | Needs to include search list of all users and view individual user | 8 | 10 | 16 |  | 0 | 0 | 0
User | Edit | 1 | 4 | 6 | 8 | 4 | Edit individual user properties. Link to edit groups | 4 | 6 | 8 |  | 0 | 0 | 0
User | Delete | 1 | 4 | 6 | 8 | 4 |  | 4 | 6 | 8 |  | 0 | 0 | 0
User Properties | CRUD User Properties | 2 | 16 | 24 | 32 |  | Edit individual user properties. Including their list of acheivements. Link to edit groups | 0 | 0 | 0 |  | 16 | 24 | 32
Timesheet | Create | 2 | 16 | 24 | 32 |  | This will be a part of the Student Portal (and mobile app) | 0 | 0 | 0 |  | 16 | 24 | 32
Timesheet | Read | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Timesheet | Edit | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Timesheet | Delete | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Event | Create | 2 | 16 | 24 | 32 |  |  | 0 | 0 | 0 |  | 16 | 24 | 32
Event | Read | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Event | Edit | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Event | Delete | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Home | Landing Page | 1 | 8 | 10 | 12 | 0 |  | 8 | 10 | 12 |  | 0 | 0 | 0
Survey | Assign | 1 | 8 | 10 | 12 | 4 | Assign a Survey to be taken by a Group | 8 | 10 | 12 |  | 0 | 0 | 0
Authentication | Change Password | 1 | 1 | 2 | 3 | 0 |  | 1 | 2 | 3 |  | 0 | 0 | 0
API | API P1 | 1 | 32 | 40 | 50 | 2 |  | 32 | 40 | 50 |  | 0 | 0 | 0
API | API P2 | 2 | 12 | 16 | 20 |  |  | 0 | 0 | 0 |  | 12 | 16 | 20
Styling | Base Template | 2 | 10 | 16 | 24 |  |  | 0 | 0 | 0 |  | 10 | 16 | 24
Styling | Home Page | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | Survey Pages | 2 | 8 | 12 | 16 |  |  | 0 | 0 | 0 |  | 8 | 12 | 16
Styling | Organizaitons Pages | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | Groups Pages | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | User Pages | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | User Properties | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | Timesheet Pages | 2 | 16 | 20 | 24 |  |  | 0 | 0 | 0 |  | 16 | 20 | 24
Styling | Event Pages | 2 | 16 | 20 | 24 |  |  | 0 | 0 | 0 |  | 16 | 20 | 24
Deployment | P1 | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Deployment | P2 | 2 | 4 | 6 | 8
|  | Priority | Best Case | Most Likely | Worst Case | Hours Left
TOTAL HOURS - DEVELOPMENT ONLY |  | All | 360 | 486 | 640
Priority 1 Only |  | 1 | 186 | 242 | 324 | 24 |  | 186 | 242 | 324 | 0 | 170 | 238 | 308 | 0
Priority 2 Only |  | 2 | 170 | 238 | 308
TOTAL HOURS WITH RESOURCES - ALL | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Senior | 100% | 20% | 72 | 97.2 | 128
Apprentice 1 | 60% | 80% | 480 | 648 | 853.3333
Apprentice 2
100%
PM |  | 20% | 72 | 97.2 | 128
Test |  | 20% | 72 | 97.2 | 128
TOTAL HOURS WITH RESOURCES- P1 Only | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Senior | 100% | 20% | 37.2 | 48.4 | 64.8
Apprentice 1 | 60% | 80% | 248 | 322.6667 | 432
Apprentice 2
100%
PM |  | 20% | 37.2 | 48.4 | 64.8
Test |  | 20% | 37.2 | 48.4 | 64.8
TOTAL HOURS WITH RESOURCES - P2 Only | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Senior | 100% | 20% | 34 | 47.6 | 61.6
Apprentice 1 | 60% | 80% | 226.6667 | 317.3333 | 410.6667
Apprentice 2
100%
PM |  | 20% | 34 | 47.6 | 61.6
Test |  | 20% | 34 | 47.6 | 61.6

## Estimation_AdminWeb_20161108
AIMS Web Admin
Time is estmate for a senior to do the work and fully unit test
Screen / Feature Name(s) | Feature Name | Priority | Best Case | Most Likely | Worst Case | Time Left | Notes | P1 B | P1 M | P1 W | P1 A | P2 B | P2 M | P2 W | P2 A
Documentation | Technical Design Document Addendum | 1 | 8 | 8 | 8 | 0 | Create TDD with screen shots | 8 | 8 | 8 |  | 0 | 0 | 0
Documentation | API Spec P1 | 1 | 16 | 16 | 16 | 4 |  | 16 | 16 | 16 |  | 0 | 0 | 0
Documentation | API Spec P2 | 2 | 16 | 16 | 16 |  |  | 0 | 0 | 0 |  | 16 | 16 | 16
Organization | Create | 1 | 8 | 10 | 12 | 0 |  | 8 | 10 | 12 |  | 0 | 0 | 0
Group | Create | 1 | 8 | 10 | 16 | 0 |  | 8 | 10 | 16 |  | 0 | 0 | 0
User | Create | 1 | 8 | 10 | 16 | 0 |  | 8 | 10 | 16 |  | 0 | 0 | 0
Authentication | Login | 1 | 8 | 10 | 16 | 0 |  | 8 | 10 | 16 |  | 0 | 0 | 0
Survey | Create | 1 | 16 | 24 | 32 | 1 |  | 16 | 24 | 32 |  | 0 | 0 | 0
Survey | Read | 1 | 8 | 10 | 16 | 1 | Display all surveys the user has created (searchable / sortable), and if an individual survey is selected, display details. | 8 | 10 | 16 |  | 0 | 0 | 0
Survey | Edit | 1 | 10 | 12 | 16 | 8 |  | 10 | 12 | 16 |  | 0 | 0 | 0
Survey | Delete | 1 | 10 | 12 | 16 | 10 |  | 10 | 12 | 16 |  | 0 | 0 | 0
Authentication | Logout | 1 | 1 | 2 | 3 | 0 |  | 1 | 2 | 3 |  | 0 | 0 | 0
Organization | Read | 1 | 4 | 6 | 8 | 0 | Display all Organizaitons (searchable), and if an individual org is selected, display details. | 4 | 6 | 8 |  | 0 | 0 | 0
Organization | Edit | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
Organization | Delete | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
Group | Read | 1 | 4 | 6 | 8 | 0 | Display all Groups, and if an individual group is selected, Display all users in the group and their roles. Admin can add users to group from here. | 4 | 6 | 8 |  | 0 | 0 | 0
Group | Edit | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
Group | Delete | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
User | Read | 1 | 8 | 10 | 16 | 0 | Needs to include search list of all users and view individual user | 8 | 10 | 16 |  | 0 | 0 | 0
User | Edit | 1 | 4 | 6 | 8 | 4 | Edit individual user properties. Link to edit groups | 4 | 6 | 8 |  | 0 | 0 | 0
User | Delete | 1 | 4 | 6 | 8 | 4 |  | 4 | 6 | 8 |  | 0 | 0 | 0
User Properties | CRUD User Properties | 2 | 16 | 24 | 32 |  | Edit individual user properties. Including their list of acheivements. Link to edit groups | 0 | 0 | 0 |  | 16 | 24 | 32
Timesheet | Create | 2 | 16 | 24 | 32 |  | This will be a part of the Student Portal (and mobile app) | 0 | 0 | 0 |  | 16 | 24 | 32
Timesheet | Read | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Timesheet | Edit | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Timesheet | Delete | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Event | Create | 2 | 16 | 24 | 32 |  |  | 0 | 0 | 0 |  | 16 | 24 | 32
Event | Read | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Event | Edit | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Event | Delete | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Home | Landing Page | 1 | 8 | 10 | 12 | 0 |  | 8 | 10 | 12 |  | 0 | 0 | 0
Survey | Assign | 1 | 8 | 10 | 12 | 8 | Assign a Survey to be taken by a Group | 8 | 10 | 12 |  | 0 | 0 | 0
Authentication | Change Password | 1 | 1 | 2 | 3 | 0 |  | 1 | 2 | 3 |  | 0 | 0 | 0
API | API P1 | 1 | 32 | 40 | 50 | 10 |  | 32 | 40 | 50 |  | 0 | 0 | 0
API | API P2 | 2 | 12 | 16 | 20 |  |  | 0 | 0 | 0 |  | 12 | 16 | 20
Styling | Base Template | 2 | 10 | 16 | 24 |  |  | 0 | 0 | 0 |  | 10 | 16 | 24
Styling | Home Page | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | Survey Pages | 2 | 8 | 12 | 16 |  |  | 0 | 0 | 0 |  | 8 | 12 | 16
Styling | Organizaitons Pages | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | Groups Pages | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | User Pages | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | User Properties | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | Timesheet Pages | 2 | 16 | 20 | 24 |  |  | 0 | 0 | 0 |  | 16 | 20 | 24
Styling | Event Pages | 2 | 16 | 20 | 24 |  |  | 0 | 0 | 0 |  | 16 | 20 | 24
Deployment | P1 | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Deployment | P2 | 2 | 4 | 6 | 8
|  | Priority | Best Case | Most Likely | Worst Case | Hours Left
TOTAL HOURS - DEVELOPMENT ONLY |  | All | 360 | 486 | 640
Priority 1 Only |  | 1 | 186 | 242 | 324 | 50 |  | 186 | 242 | 324 | 0 | 170 | 238 | 308 | 0
Priority 2 Only |  | 2 | 170 | 238 | 308
TOTAL HOURS WITH RESOURCES - ALL | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Senior | 100% | 20% | 72 | 97.2 | 128
Apprentice 1 | 60% | 80% | 480 | 648 | 853.3333
Apprentice 2
100%
PM |  | 20% | 72 | 97.2 | 128
Test |  | 20% | 72 | 97.2 | 128
TOTAL HOURS WITH RESOURCES- P1 Only | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Senior | 100% | 20% | 37.2 | 48.4 | 64.8
Apprentice 1 | 60% | 80% | 248 | 322.6667 | 432
Apprentice 2
100%
PM |  | 20% | 37.2 | 48.4 | 64.8
Test |  | 20% | 37.2 | 48.4 | 64.8
TOTAL HOURS WITH RESOURCES - P2 Only | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Senior | 100% | 20% | 34 | 47.6 | 61.6
Apprentice 1 | 60% | 80% | 226.6667 | 317.3333 | 410.6667
Apprentice 2
100%
PM |  | 20% | 34 | 47.6 | 61.6
Test |  | 20% | 34 | 47.6 | 61.6

## Estimation_AdminWeb_20161024
AIMS Web Admin
Time is estmate for a senior to do the work and fully unit test
Screen / Feature Name(s) | Feature Name | Priority | Best Case | Most Likely | Worst Case | Time Left | Notes | P1 B | P1 M | P1 W | P1 A | P2 B | P2 M | P2 W | P2 A
Documentation | Technical Design Document Addendum | 1 | 8 | 8 | 8 | 0 | Create TDD with screen shots | 8 | 8 | 8 |  | 0 | 0 | 0
Documentation | API Spec P1 | 1 | 16 | 16 | 16 | 4 |  | 16 | 16 | 16 |  | 0 | 0 | 0
Documentation | API Spec P2 | 2 | 16 | 16 | 16 |  |  | 0 | 0 | 0 |  | 16 | 16 | 16
Organization | Create | 1 | 8 | 10 | 12 | 0 |  | 8 | 10 | 12 |  | 0 | 0 | 0
Group | Create | 1 | 8 | 10 | 16 | 0 |  | 8 | 10 | 16 |  | 0 | 0 | 0
User | Create | 1 | 8 | 10 | 16 | 0 |  | 8 | 10 | 16 |  | 0 | 0 | 0
Authentication | Login | 1 | 8 | 10 | 16 | 0 |  | 8 | 10 | 16 |  | 0 | 0 | 0
Survey | Create | 1 | 16 | 24 | 32 | 1 |  | 16 | 24 | 32 |  | 0 | 0 | 0
Survey | Read | 1 | 8 | 10 | 16 | 1 | Display all surveys the user has created (searchable / sortable), and if an individual survey is selected, display details. | 8 | 10 | 16 |  | 0 | 0 | 0
Survey | Edit | 1 | 10 | 12 | 16 | 8 |  | 10 | 12 | 16 |  | 0 | 0 | 0
Survey | Delete | 1 | 10 | 12 | 16 | 10 |  | 10 | 12 | 16 |  | 0 | 0 | 0
Authentication | Logout | 1 | 1 | 2 | 3 | 0 |  | 1 | 2 | 3 |  | 0 | 0 | 0
Organization | Read | 1 | 4 | 6 | 8 | 0 | Display all Organizaitons (searchable), and if an individual org is selected, display details. | 4 | 6 | 8 |  | 0 | 0 | 0
Organization | Edit | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
Organization | Delete | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
Group | Read | 1 | 4 | 6 | 8 | 0 | Display all Groups, and if an individual group is selected, Display all users in the group and their roles. Admin can add users to group from here. | 4 | 6 | 8 |  | 0 | 0 | 0
Group | Edit | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
Group | Delete | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
User | Read | 1 | 8 | 10 | 16 | 0 | Needs to include search list of all users and view individual user | 8 | 10 | 16 |  | 0 | 0 | 0
User | Edit | 1 | 4 | 6 | 8 | 4 | Edit individual user properties. Link to edit groups | 4 | 6 | 8 |  | 0 | 0 | 0
User | Delete | 1 | 4 | 6 | 8 | 4 |  | 4 | 6 | 8 |  | 0 | 0 | 0
User Properties | CRUD User Properties | 2 | 16 | 24 | 32 |  | Edit individual user properties. Including their list of acheivements. Link to edit groups | 0 | 0 | 0 |  | 16 | 24 | 32
Timesheet | Create | 2 | 16 | 24 | 32 |  | This will be a part of the Student Portal (and mobile app) | 0 | 0 | 0 |  | 16 | 24 | 32
Timesheet | Read | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Timesheet | Edit | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Timesheet | Delete | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Event | Create | 2 | 16 | 24 | 32 |  |  | 0 | 0 | 0 |  | 16 | 24 | 32
Event | Read | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Event | Edit | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Event | Delete | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Home | Landing Page | 1 | 8 | 10 | 12 | 1 |  | 8 | 10 | 12 |  | 0 | 0 | 0
Survey | Assign | 1 | 8 | 10 | 12 | 8 | Assign a Survey to be taken by a Group | 8 | 10 | 12 |  | 0 | 0 | 0
Authentication | Change Password | 1 | 1 | 2 | 3 | 0 |  | 1 | 2 | 3 |  | 0 | 0 | 0
API | API P1 | 1 | 32 | 40 | 50 | 10 |  | 32 | 40 | 50 |  | 0 | 0 | 0
API | API P2 | 2 | 12 | 16 | 20 |  |  | 0 | 0 | 0 |  | 12 | 16 | 20
Styling | Base Template | 2 | 10 | 16 | 24 |  |  | 0 | 0 | 0 |  | 10 | 16 | 24
Styling | Home Page | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | Survey Pages | 2 | 8 | 12 | 16 |  |  | 0 | 0 | 0 |  | 8 | 12 | 16
Styling | Organizaitons Pages | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | Groups Pages | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | User Pages | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | User Properties | 2 | 4 | 6 | 8 |  |  | 0 | 0 | 0 |  | 4 | 6 | 8
Styling | Timesheet Pages | 2 | 16 | 20 | 24 |  |  | 0 | 0 | 0 |  | 16 | 20 | 24
Styling | Event Pages | 2 | 16 | 20 | 24 |  |  | 0 | 0 | 0 |  | 16 | 20 | 24
Deployment | P1 | 1 | 4 | 6 | 8 | 0 |  | 4 | 6 | 8 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 1 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Deployment | P2 | 2 | 4 | 6 | 8
|  | Priority | Best Case | Most Likely | Worst Case | Hours Left
TOTAL HOURS - DEVELOPMENT ONLY |  | All | 360 | 486 | 640
Priority 1 Only |  | 1 | 186 | 242 | 324 | 51 |  | 186 | 242 | 324 | 0 | 170 | 238 | 308 | 0
Priority 2 Only |  | 2 | 170 | 238 | 308
TOTAL HOURS WITH RESOURCES - ALL | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Senior | 100% | 20% | 72 | 97.2 | 128
Apprentice 1 | 60% | 80% | 480 | 648 | 853.3333
Apprentice 2
100%
PM |  | 20% | 72 | 97.2 | 128
Test |  | 20% | 72 | 97.2 | 128
TOTAL HOURS WITH RESOURCES- P1 Only | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Senior | 100% | 20% | 37.2 | 48.4 | 64.8
Apprentice 1 | 60% | 80% | 248 | 322.6667 | 432
Apprentice 2
100%
PM |  | 20% | 37.2 | 48.4 | 64.8
Test |  | 20% | 37.2 | 48.4 | 64.8
TOTAL HOURS WITH RESOURCES - P2 Only | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Senior | 100% | 20% | 34 | 47.6 | 61.6
Apprentice 1 | 60% | 80% | 226.6667 | 317.3333 | 410.6667
Apprentice 2
100%
PM |  | 20% | 34 | 47.6 | 61.6
Test |  | 20% | 34 | 47.6 | 61.6

## Libraries
Library Name | Priority | Notes

## Images
Images Needed
Screen | Image | Notes

## Version History
Version | Date | Author | Notes
1 | 2015-01-04 |  | Initial Draft
2
3
4
5
6

## References
Reference Name | Location | Filename / Notes